## Slide 1: Effective Project Planning & Managing Change: How States Handle Unexpected Changes
Monday, October 29, 2012
Facilitators: Robin Taylor (SST) & Jeff Sellers (SST)
Panelists:
Tom Fontenot, & Matt Brownlee, District of Columbia Office of the State Superintendent of Education
Christina McDougall, Washington State Education Research & Data Center
Melissa Straw, Wisconsin Department of Public Instruction

## Slide 2: Overview
1) Overall project description and background
2) Description of issues each state has encountered
3) Importance of Project Planning
4) How to deal with Project Change
5) How to deal with Vendor Termination
6) Build vs. buy
7) Performance management
8) Effect of funding constraints
9) Effect of political and legal constraints

## Slide 3
Project Background

## Slide 4: Washington, DC
  The Statewide Longitudinal Education Data (SLED) System will serve as a single, comprehensive repository of current and historical student and education-related data.
  SLED will facilitate intra-governmental data-driven decisionmaking.
  SLED will provide community stakeholders with relevant, aggregate student information and trends.

## Slide 5: Wisconsin
SLDS Grants Dashboards and Reporting
Dashboards and Reporting
Public Reporting Current=WINSS Future=WISEdash
Performance Report Cards (SDPR)
Secure Home
ASM
WISEmaps
MDAT
MDAT Training
SAFE
WISEdash

## Slide 6: Wisconsin
DPI purchased a suite of data, dashboard, and reporting tools
  Data Model & Dashboard from VersiFit Technologies
    Based in Appleton
    Serves MMSD, MPS, Chicago Public Schools, Oregon State, Hawaii, etc.
    Focus on business intelligence solutions specific to education
    Contract signed 02/16/11
  ETL and Reporting tools from Microsoft
    Reporting tool will also be utilized throughout the agency for operational reporting.
  The LDS ODS is now currently being used as a data store as we transition to our new data warehouse system.
  Wisconsin Information System for Education Dashboard solution
  or WISEdash, powered by Edvantage
SLDS Grants Next Generation Data, Dashboards, Reporting

## Slide 7: Wisconsin
WISEdash, powered by Edvantage
Education data model structured to enable smart, reporting on education data
  Store and link student and school data from a variety of sources including collection systems, spreadsheets, and external files for reporting and analysis
    Enrollment data, test scores, student growth, graduation, postsecondary enrollment
Role based data access & dashboards
Public & secured reporting through the same technology to a wide variety of users with a wide variety of data needs
Simple ad hoc reporting functionality (choose a district, choose a demographic)
Advanced reporting capabilities for a limited number of power users at the district and state level to create customizable reports
Documentation, including professional development resources such as pre-made workbooks to guide understanding and use of dashboards and reports
Opportunity for collaboration, already used by MMSD and MPS in Wisconsin

## Slide 8: Washington
Washington’s 20W Program
Office of Financial Management’s Education Research and Data Center – oversees the Program, permanent home of P-20W
  Collects, processes, maintains and provides P20W longitudinal data
  Performs P20W Research and Reporting
Consists of 9 overall projects
P20W Data Governance
P20W Research and Reporting
  ERDC
    3 P20 Feedback Reports – K12, CTCs and Baccalaureates
    5 Education and Teacher Briefs
    Data Sets
  Department of Social and Health Services
    5 Briefs – Education Outcomes of Social Services Recipients
P20W Data Warehouse Implementation
Source System Implementation/Enhancements – 5 projects
  Early Childhood – Implementation
  Public Higher Education – Enhancement
  Washington Student Achievement Council (4 -Years Council) – Enhancement
  State Board for Community and Technical Colleges ) – Implementation
  Workforce and Technical Education College Board – Implementation

## Slide 9: Washington
Data Warehouse Implementation Project
Custom Data Model, In-House Build with purchased software tools and some technical support services
1) Creating Washington State’s P20W longitudinal data model and reporting capability
  Unique Data Model Based on Person, Role Organization
2) Loading Historical Data into P20W Data Warehouse and Model
  Early Childhood – Early Childhood Education and Assistance Program
  K-12 – Student, Teacher, Enrollment, Assessments, Financial
  Higher Ed – 4-Years, CTCs, National Student Clearinghouse
  Work force – UI Wage
  Look-up Tables (Social Security, Department of Licensing, Administrative Office of the Courts, etc.)
Automating On-Going Processes and Additional Data Sources
  Electronic Transfers and Loads of recurring data, Identity Matching and Linking, Data Quality, Limited Report Generation
  Dept of Corrections, Dept of Revenue, Additional Early Childhood, etc.
Providing Limited Access to Specific Data
  For Data Partners (EC, Higher Ed, K-12, Workforce)
  To Specific Data Sets

## Slide 10
Issues Encountered

## Slide 11: Washington, DC
  IT Driven vs. Business/Program Driven
  Management Turnover (all levels, Mayor to SLED Director)
  Vendor Performance
  Contract Termination
  Procurement (slowness)
  Scope Creep (marketing)

## Slide 12: Wisconsin
Purchase, Initial Sole Source, Additional Sole Source
Waiver & Sole Source Approval
Scope Change
Staffing Changes
  ETL Lead, Dashboard Technical Lead, Security Lead, PM
  ETL vs. Dashboard Team Members
  Management Team
  Content Areas
Entire project lifecycle, including architecture
Staff Training, learning curve
Communication
Rollout

## Slide 13: Washington
Washington State Legislature
  2011 Bill to eliminate the ERDC and move functions to another organization
  Bill passed the Legislature, vetoed by the Governor
State Consolidation of IT Services
  Removed all of OFM’s IT services and consolidated into a new, separate agency
  Turnover of most of the IT staff on the project
  New IT Leadership
  New agency growing pains – shuffling staff, new processes and procedures
P20W Data Warehouse Project Manager
  First vendor was made the Technical Manager
  Second vendor was not a good fit and terminated for convenience
  Success with a state staff Project Manager
4) P20W Data Warehouse Software and Technical Services Vendor
  After contracting with a vendor with reservations, the Program determined the software was not a fit
  Terminated the contractor for convenience
  Pursuing an in-house build employing off-the-shelf data quality, data movement, and identity matching software tools and technical services support

## Slide 14
Project Planning

## Slide 15: Washington, DC
Be prepared
Review often
Adjust accordingly
Spend the time upfront in order to “Be Prepared”

## Slide 16: Wisconsin
Importance of Project Planning
Certain roles must be filled
  Business and IT Sponsor, Project Manager, Education Consultant
  Team member for communication and training
Initial Plan, Realistic Dates
Project Charter to set expectations
Roles, Responsibilities
Communication Plan
Training Plan
Using Agile Post-Implementation

## Slide 17: Washington
Risk and Issue Management
Regular, structured risk and issue management meetings to identify:
    “What Ifs”
    Mitigation Strategies and Plan B’s
    How do we know when a risk has turned into an issue?
      What are the signs and triggers?
When to create Plan B
  Planning takes time, resources
  Risk and Issue Management provide for estimating the probability a risk will turn into an Issue
  When the Issue probability is large enough for Plan A, ensure there is a Plan B (or C, D and E…)
Knowing when Plan B is triggered
  Sometimes it’s before Plan A has completely fallen apart
Communication
No Surprises
Stakeholders
  are aware of the Risks and Issues
  agree on Mitigation Strategies and Triggers
  approve of Plan B
Turns potentially huge issues closer to non-events
Flexibility
Ability to recognize opportunities
Ability to take advantage of them (new opportunity or turning a failed one into a new one)

## Slide 18
Project Change

## Slide 19: Washington, DC
Plan
Adjust
Communicate
  Structured & Documented
Be formal
Change in leadership

## Slide 20: Wisconsin
How to deal with change
Plan for It (it will happen!)
Energy
Dedication
Positive attitude
Honest communication and transparency
Reviewing project plans and scope, adjust as necessary
Supporting documentation

## Slide 21: Washington
Handling the Immediate Impact of Large Change
Communication of Change
Create the plan of who to tell what, when and by whom
Schedule it out
Craft messaging
Give Staff the opportunity to voice concerns
Identify and Plan the Wrap-Up Activities
Haphazard communication of change and follow-up activities
Perception of poor treatment
Feeling of disorganization

## Slide 22
Vendor Termination

## Slide 23: Washington, DC
Have a Plan/Strategy
Communication (internal and external)
Hire an independent auditor
Document, Document, Document
Ensure that contracts are deliverable based (defined, detailed, and date-driven)
Re-Procurement Dead Time: Progress or Die
Cost (legal and restart)

## Slide 24: Washington
How to keep momentum going when there’s been a vendor termination
What does Plan B need to contain?
What, if anything, can be re-used from Plan A solution’s completed work?
Identify those activities and parts of the original plan that are solution neutral
  What allows you to pivot to a different solution without starting completely over?
    Business Activities: Data Governance, Data Analysis, Data Readiness, Designing the data model, Data Mapping
    IT: Purchase and Install Infrastructure Components
  Flexibility counts
If possible – identify what the Plan B solution is
  Identify next steps and details toward obtaining and pursuing the new solution
Start with Plan A – If Plan A has a high level of risk, build these mitigations into it
Transparency
Ongoing, good communication to stakeholders
No surprises

## Slide 25
Build vs. Buy

## Slide 26: Washington, DC
Cost
Sustainability
Community Support from a COTS product
Quick deployment
A mature COTS product should provide configuration flexibility
  Large user base drives compliance of the COTS to the latest changes in the market.
COTS lock you into a vendor product and support model
Build provides the flexibility to adapt the program to changes
Build requires an investment in a development staff and infrastructure

## Slide 27: Wisconsin
Buy
A solution, not a tool or application
Sustainability
Staffing
Scalability statewide
Efficiency – eliminates redundant time needed to manage these systems in every district and multiple systems at the state level
Equity – every school district, teacher, and parent the same data tools equitably
Quality – because the data are consistent higher quality data are used for decisionmaking

## Slide 28: Washington
Consider State’s Current Environment
Where will the P20W SLDS system reside?
  Within a specific sector-based organization with an existing transaction-based SLDS?
  Within a P20W or other non-sector organization without operational activities?
  Is this an existing organization with strong relationships or a new organization needing to build relationships with P20W sectors?
Decentralized vs. Centralized Education Agencies/System
  Where does the data reside?
  How easy will it be to obtain P20W data given the state education system?
What is your approach to longitudinal data?
  Use of a system-wide unique identifier or multiple identifiers?
  Need for an individual’s “Golden Record” or the need to keep all information across time and sectors on an individual

## Slide 29: Washington
Consider P20W Solution Risks and Opportunities in light of State’s Current Environment
How best can we mitigate risks from and with a combination of these solutions?
Build or Buy?
Buy Commercial Off-the-Shelf Product
  P20W is not like a payroll or human resources system – where there are multiple mature products on the market
  How closely do the current products match our business and technical requirements?
    Longitudinal data model, Robust Identity Matching and Linking, Flexible Cohort Selection and Maintenance, Ease of maintenance and extensibility
  Can we leverage the functionality of current products and the knowledge of their creators?
In-House Build with Purchased Software Tools
  Are our requirements not met by a single COTS product?
  Will commercial software tools needed to build in-house fit our requirements?
  Do we have the business and technical skill sets, experience, resources to build in-house using these tools?
  How best to obtain those skills that we don’t have?
How to implement?
Implementation Vendors
  Do we need the full host of vendor services? (PM, technical expertise, business analysis, etc.)
  Allows more risk to be taken on by the vendor
  Can be very expensive and Still requires a lot of state resources
Hybrid - with State and Vendor Support Services
  What skill gaps do we need the vendor to fill in order to build in-house?

## Slide 30
Performance Management

## Slide 31: Washington, DC
Set Clear Goals that are attainable
Review often
Make adjustments based on real life data
Develop a strategic plan
Invest in strong requirements
CLIN based contacts with incremental acceptance points
Executive ownership and decision makers

## Slide 32: Wisconsin
Communicate throughout all levels of the organization and with external customers
Engage Stakeholders
Communicate between projects
Ensure transparency
Set expectations
Use Agile Methodology
Manage Scope
Involve project team early on, meet as needed to ensure teamwork and collaboration
Manage meeting participation
Team or Product Champion (different than sponsor)

## Slide 33: Washington
Setting both the state and the vendor up for success in achieving goals
Ensure vague terms are defined
What does “Data Readiness” mean?
Define deliverables (Deliverable Expectation Documents)
Set reasonable goals, schedule and milestones
Requires having and articulating a true picture of the work and the level of effort required to accomplish it
  What are the steps involved between obtaining data and having it accessible in a data warehouse?
What are the vendor’s expectations of the state?
What are the expectations of the business?
  Does the business understand this?
What is the Post-Implementation Plan?
Set expectations
Proactive Communication (over and over)

## Slide 34
Funding Constraints

## Slide 35: Washington, DC
Phased Approach
Build it and they will come!
Ability to say NO
Constraints impact the flow of the contract
They impact the order of completion and deployment

## Slide 36: Wisconsin
To date all work has been almost entirely SLDS grant funded
Continue to write grants
Included Data Warehouse and Decision Support in DPI’s Biennial Budget Request

## Slide 37: Washington
Washington has been able – and anticipates continuing – to accomplish the work with the Grant
Washington’s Primary constraint has been schedule
ARRA Grants 3-year timeframe, ending date of 6/30/2013
Still planning for 6/30/2012
1-Year Extension – to be evaluated if/when available

## Slide 38
Political/Legal
Constraints

## Slide 39: Washington, DC
Multiple Agendas
Data Sharing (MOUs and NDAs for everyone)
Snowball Effect

## Slide 40: Wisconsin
Legal
  Lack of consistency internally about interpretation of FERPA and ownership / responsibility of LEA data
  Challenges aligning the district legal interpretations of FERPA with DPI
  Educating partners like CESAs on FERPA
  P20 Postsecondary and P20 Early Childhood data governance and data sharing with partners
Political
  WISEdash is being rolled out at the same time as the new accountability system
  Large budget cuts to districts
  Competing interests between agency leadership, legislature, and governors office around priority
  Many other agency projects and reforms occurring at the same time

## Slide 41: Washington
Political
Typical Legislative and Agency Activities
Heavy oversight of our project
  3 Executive Sponsors – each in a different reporting structure
    Governor, Legislative, Elected Official
  Quality Assurance Vendor (reports to sponsors and OCIO)
  State’s Office of the Chief Information Officer’s Liaison to project
Legal
Privacy laws
  Lack of clarity
  Slowness of clarifications
    National and State level

## Slide 42: Contacts & Additional Resources
Contact information:
Melissa Straw, Melissa.Straw@dpi.wi.gov
Christina McDougall, Christina.McDougall@OFM.WA.GOV
Tom Fontenot, thomas.fontenot@dc.gov
Matt Brownlee, matthew.brownlee@dc.gov
Robin Taylor, robin.taylor@sst-slds.org
Jeff Sellers, jeff.sellers@sst.org
Additional Information:
  DPI LDS Project – www.dpi.wi.gov/lds
  SDPR – https://apps2.dpi.wi.gov/sdpr/spr.action
  WISEmaps - https://wisemaps.dpi.wi.gov/
  WISEdash - http://dpi.wi.gov/lds/dashhome.html